## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: VaultShield: Sandboxed, Monitored Execution and Human Review for AI Coding Agents | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Prof. Rajashri Chaudhari, Prof. Hardiki Achrekar | [6 empty] | DATE: 15/10/2026
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Major Project | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-07-10 | 2026-07-17 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.2 | Discussing the project topic with the help of paper prototype. | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-07-17 | 2026-07-24 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
1.3 | Identifying the functionalities of the Major Project as per the objectives identified | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-07-24 | 2026-07-31 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.4 | Literature review and research paper study | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-07-31 | 2026-08-07 | 1 | 100% | bar: WEEK 4 M to WEEK 5 F
1.5 | Designing the Graphical User Interface (GUI) | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-08-07 | 2026-08-28 | 3 | 100%
1.6 | Presentation I | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-09-04 | 2026-09-04 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F
2 | Project Design and Implementation
2.1 | Policy Logic Development | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-09-18 | 2026-09-25 | 1 | 100% | bar: WEEK 7 M to WEEK 7 F
2.2 | Core Model Development and Training | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-09-25 | 2026-10-01 | 1 | 100% | bar: WEEK 8 M to WEEK 8 F
2.3 | Presentation II | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-10-09 | 2026-10-09 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
3 | Project Evaluation and Documentation
3.1 | Incorporating the changes as per suggestions in presentation II and submission of a draft copy to project guide for proof reading | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-10-16 | 2026-10-23 | 1 | 100% | bar: WEEK 10 M to WEEK 10 F
4 | Final Submission and Enhancement
4.1 | Draft submission to guide for review and final blackbook submission | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-10-23 | 2026-10-24 | 1 | 100% | bar: WEEK 11 M to WEEK 11 F
4.2 | Final blackbook submission | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-10-26 | 2026-10-30 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F
4.3 | External Presentation and Viva voce | Aayush Balip, Sameer Saiyed, Krish Patil, Mohammad Momin | 2026-11-02 | 2026-11-02 | 1 | 100%